## Sheet1
Date | Request | Question | By | Response | Add
2023-07-10 | Legend Theatrical
|  | It looks like this is for the purchase and installation of the FFE bill of materials only, can you confirm that? This is not a bid on the greater overall project. |  | This is correct.
|  | Is this project a prevailing wage project or are there any existing PLA or Union agreements in place we need to be aware of? |  | This is a prevailing wage project.
3
|  | Will this contract be direct with owner (the college) or will it be sub to a General Contractor? I am assuming direct if it is all FFE. |  | Direct to Owner
2023-07-17 | AV Meeting |  |  |  | 3
|  | References: There are some references to a existing system. IE QCS Software. It’s a all-new system. |  | The software to the existing system must be modified for the added audio equipment.
|  | Is it QSC 110 or 510 system? |  | Yes, the QSC 510i is existing
|  | Is there a QSC Processor in the scope of this work? |  | No, Processor is existing
|  | Are there elements which are shown as existing that should all be referred to as new? If there are some existing systems, it should be in the single line. |  | The existing system are on the single lines.
|  | Is there OFOI or OFCI installed equipment for this scope to coordinate? |  | No, all contractor installed, no Owner Furnished Equipment.
|  | Note: District is not planning on doing any installations for this project. |  | They don’t have to install, most equipment is miscellaneous for events. | 3
|  | Per Dave Willis, Addendum should include a statement “Bidders may amend Exhibit A of bid form as required” |  | Please bid on the specificed equipment listed items in Exhibit A on the bid Form. Please update the equipment items as needed if a manufacturer no longer offers the specified equipment item. Otherwise, please only bid what is specified. Indicate the lead times from order date to ship date for each item. | 3
3
2023-07-24 | Bianca Montalvo |  |  |  | 3
|  | Section 01 61 00, “Bid Form”, there is only BID form section 00 41 00, can you please provide or let us know if BID Form 00 41 00 is suffice. |  | Yes, specification 00 41 00 is the Bid Form that is required with this project.. Yes, a Bid Bond is required for this project. | 3
3
|  | If we have lead times for BOM items, would you hold it to complete the contract Dec. 8 2023? Or can we have tentative date of Dec. 2023? |  | If the manufacturer lead-times do not allow the completion of the project by December 8, 2023, the District will allow completion at a later date in the month of December. Please do everything possible to complete the project scope in early December. Please note any concerns regarding lead-times in your proposal. | 3
2023-07-25 | Terra Yang | Denon DN-500BD (discontinued) to Denon DN-500BD MKII (new one) |  | Yes, the replacement unit is acceptable.
2023-07-31 | David Willis | The Proposal Due date and Time has been Changed to Monday, August 7th, 2023, 3pm Sharp. |  | Proposal Due dateand time changed.
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3