## Sheet1
Date | Request | Question | By | Response | Add
2023-06-09 | Tina Shibata
|  | Is the kitchen equipment shown on the drawings and spec book that say by others or noted by GC is by a GC and not a kitchen subcontractor. |  | Correct
2023-07-06 | Lathrop Conctruction
|  | Please provide a list of attendees of the two Zoom Optional Pre-Bid Conference Meetings |  | Since these were optional pre-bid meetings, this information was not recorded. | 3
|  | In the July 5th Pre-Bid Conference meeting, it was mentioned that a more detailed bid sheet, with each item in the bid individually priced, would be issued in Addendum 2 on Tuesday July 12th. We recommend that this information be provided within 48 hours of the bid date. The amount of information that would be needed to be completed on bid date to meet this requirement will be cumbersome and could lead to incomplete bids or bids that do not meet the District’s requirements. |  | see attached detailed bid sheet under Addendum 2
3
|  | Please confirm that the items shown as ‘future’ in the Equipment Schedules (sheets FS-201 thru FS-204) are not included in this bid pricing. Examples include 2-04 thru 2-06, 2-11 thru 2-2-17, 2-20 thru 2-24, 3-34, 3-36. There are no specs for these items in the 11 4000 specification but they do show up on the plan views. These items were not addressed in Addendum . |  | Refer to specifications provided in Addendum 1 for items included in the biud pricing. Missing items from specsifications provided in Addendum 1 denotes "not in the FFE culinary package" | 3
3
|  | The download link in spec 11 4000, item 1.1J (page 2) does not work. Please provide new link for the Schedule of Values if we need to use that. |  | The noted Schedule of Values is provided directly. | 3
3
|  | Please confirm that “Group 2” furniture IS to be included in this bid package. In the Zoom meeting on July 5th, it was noted that “Group 2” is the same as the “FF&E” included in this bid package. The first paragraph of spec 11 4000, item 1.1A, states that Group 2 will be bid separately. This question would also apply to Addendum 1. |  | Confirmed "Group 2" furniture is included in this bid package | 3
3
|  | Spec 11 4000 item 1.2 references Division 5, 6, 23, 26 and 28 specification sections which were note issued with these bid documents. We will need those. |  | Provided | 3
|  | Need more details/drawings for the NIFSEC Items that are to be priced this this bid (example 1-198, 3-23, 3-24) |  | NIFSEC not included in this bid package
|  | Need to confirm that NIFSEC items “by vendor” (example includes # 3-43) are not to be furnished or installed in this bid |  | Correct
|  | Need to confirm that NIFSEC items “by owner” (example includes # 3-41) are no to be furnished or installed in this bid |  | Correct
|  | Per Addendum 1 items 1-117, 1-120, 1-124 and 1-127 are included in this bid. We need a specs for those items |  | See pages 83-86 of Addendum 1
|  | Will new sheets FS 201 thru FS 204 be issued to reflect Addendum 1 changes? |  | No
|  | These items are on sheet FS-302 and in the equipment list but not included in the specs: 1-15, 1-16, |  | Missing items from specsifications provided in Addendum 1 denotes "not in the FFE culinary package"
|  | The count on wine shelves 2-02 and 2-03 in the Walk In cooler appear to not match up with counts on these items in the specs. Specs show 3 of one, 3 of the other. Drawing shows 2 of 2-02 and 4 of 2-03? |  | See equipment schedule on FS-204. It shows 3 of 2-02 and 3 of 2-03 | 3
3
|  | Confirm that shelves 1-26 are not to be included in this price |  | Confirmed. Missing items from specsifications provided in Addendum 1 denotes "not in the FFE culinary package"
|  | Utility chase 1-218: One is listed in the specs but two are shown on FS-102 |  | See equipment schedule on FS-203. It shows 1 of 1-218. The Utility chase was tagged twice on the FS-102 | 3
|  | Specs call for one of the 3-33 items. But drawing FS-102 shows 3 of them. Which is correct? |  | See equipment schedule on FS-204. It shows item 3-33 having 4. Also see 5/FS-703 | 3
2023-07-07 | Lathrop Conctruction |  |  |  | 3
|  | Please confirm that this project does not have an Owner Furnished Insurance Program (OCIP). |  | There is no Owner Furnished Insurance Program on this Culinary Equpment project. Contractors need to provide their own insurance like they would on a typical project. | 3
|  | In regard to the Section 00 52 00 Contractor Agreement for Services Appendix B Insurance: Paragraph 5 says “If Applicable”. Is paragraph 5 applicable, is Builder’s Risk insurance required? What about “Alternatively, if applicable”?? Please clarify these requirements. |  | Since the new building will be secured with locked doors by the time the equipment arrives, builders risk insurance is not required.
|  | Section 01 50 00 Temporary Facilities and Controls says NOT APPLICABLE. If this section is not applicable, then will the District be providing the items described in this section such as temporary sanitary facilities, temporary access, progress cleaning, temporary protection, storage areas, security, etc. |  | Temporary restroom facilities are required. Otherwise, the building will be built, spaces secured, and ready for the equipment to be set in place when delivered after November 1, 2023.
|  | Section 01 77 19 Close out Requirements says NOT APPLICABLE. If this section is not applicable, then will the District be providing the items described in this section such as final cleaning? |  | Section 01 77 19 applies to this project. Final cleaning shall be provided. | 3
3
|  | Section 00 41 00 Bid Form states that all equipment must be delivered by December 1, 2023. Since some food service items have lead times of at least 3 months, after approved submittals, it is likely that some equipment will not be delivered until late December or sometime in January. As noted in the pre bid meeting, please confirm the latest delivery period for equipment would be just prior to occupancy the third week of January. |  | All equpment must be delivered and installed as soon as possible. Classes are scheduled to begin on January 16, 2024. The Kitchen area will need to have reached Substantial Completion before this date. It will take a several weeks to get all of the required permits with the Yolo County Department of Health, and other agencies. All equipment must be set in place no later than December 18, 2023. | 3
3
|  | Section 11 40 00 states that the warranty period is 1 year from the date of substantial completion. Section 00 65 36 states the warranty period is 2 years. Please confirm which is correct. |  | The 2 year warranty period is correct.
2023-07-10 | Lathrop Conctruction
|  | The Bid bond form references at New Softball Field project and will need to be updated for this Culinary project. Thank you |  | Updated. | 3
3
3
3
3
3
3
3
3
3